## Specify Project Requirements
Project Requirements
S. No. | Requirement/ Feature | Completed
1 | To at least give an good and useful output | Yes
2 | To be very user-friendly with nonspecialized clients | Yes
3 | To give addition information on the website using the same dataset | Yes
4 | Feedback form to know how to app performs and further improve functioning and features | Yes

## Features
S No | Features
1 | Data Inputting by User
2 | Data Formating Algo that works for most datasets
3 | Quick Prediction Model w/High accuracy
4 | Time Series Analystics based on ARIMA
5 | Elangantly formatted output for easy viewing
6 | Feedback form to review and further enchance app

## Sprints
S No | Sprint | Start Date | End Date
1 | Sprint 1 | 27/6/23 | 27/6/23
2 | Sprint 2 | 27/6/23 | 27/6/23
3 | Sprint 3 | 27/6/23 | 28/6/23
4 | Sprint 4 | 28/6/23 | 28/6/23
5 | Sprint 5 | 28/6/23 | 29/6/23
6 | Sprint 6 | 28/6/23 | 29/6/23
6 | Sprint 7 | 29/6/23

## Sprint-Features Mapping
S No | Sprint | Features
1 | Sprint 1 | Choosing multiple datasets of different varieties and going through main features of them
2 | Sprint 2 | Developing a fuction that can clean, pre-process any given dataset.
3 | Sprint 3 | Performing EDA and visualization
4 | Sprint 4 | Time based analysis on Web Log Data
5 | Sprint 5 | Time Series Analytics using ARIMA
6 | Sprint 6 | User Interface Design
7 | Sprint 7 | Testing & Review

## Algorithm
In this project, the algo being used is ARIMA. The reason why ARIMA is choosen is because it is a statistical model which it predicts future values based on past values. This is ideal for our project as we are give various log data, such as IP addresses, timestamps, URLs, user agents, and response codes, which can be understood very well by our model and then be used to predict what could be future values.

## Event Handlers
Event Handlers Matrix
S. No. | Element | Action | What happens?
1 | t&c | "checkbox" | At the begining of the page a closable element with the terms and privacy policy along with an option to agree and diagree will appear
2 | uploadFiles-button | “click” | Prints the data on the screen and presents a graph on the data right below it
3 | data-visual | - | After the user uploads the data a small column comprising of the data will be preseted in an interactive chart for the user to work with.
4 | web-info | - | Along with the graph a concise information on the website will be generated for the given dataset will be displayed for user to do his appropriate actions on it
5 | pred-input | "input" | After giving prediction value, ARIMA model processes the data and the rest of the results come up on the screen along with the graph
6 | feedback | "choose/input" | At the end of the project (after forcasting) a feedback form with a rating along with a comment section appears

## Test Plan
Test Plan
S. No. | Element | What happens? |  | Tested | Results | Pass/ Fail | Corrected
1 | t&c | "checkbox" | At the begining of the page a closable element with the terms and privacy policy along with an option to agree and diagree will appear
2 | uploadFiles-button | “click” | Prints the data on the screen and presents a graph on the data right below it | Yes | Working as expected | Pass
3 | data-visual | - | After the user uploads the data a small column comprising of the data will be preseted in an interactive chart for the user to work with. | Yes | Working as expected | Pass
4 | web-info | - | Along with the graph a concise information on the website will be generated for the given dataset will be displayed for user to do his appropriate actions on it | Yes | Working as expected | Pass
5 | pred-input | "input" | After giving prediction value, ARIMA model processes the data and the rest of the results come up on the screen along with the graph | Yes | Working as expected | Pass
6 | feedback | "choose/input" | At the end of the project (after forcasting) a feedback form with a rating along with a comment section appears | Yes | Working as expected | Pass